## read this first
In all sprints, frontend functions and the connected backend functions must be developed at the same time so that they can be tested before the sprint can be considered as completed
All sprints will later be broken down to tickets and assigned to the coders
The Wordpress installation is mainly meant to handles pages, and posts, while all sales functions must be handled outside Wordpress but integrated to be displayed on the relevant pages in the Wordpress frontend.
Pages and Posts translations will be handled in Wordpress
All text for sales functions etc. which is managed in the operator backend must be translatable as well! Either we integrate some of that text in Wordpress, or we must have a file containing all text pieces managed in the backend, which can be given to a translator, and then the file gets imported to the backend again. Possibly, poedit can be used for this: https://poeditor.com/
User experience is paramount. Frontends and backends must be responsive with dedicated layouts for phone, tablet and desktop/laptop
Also, the platform should be built so that it can easily be cloned and installed on other domains. We may offer a B2B service for other operators later.
Find a video with a short overview of the frontend functions here:
https://www.loom.com/share/0626df2d529247d891433c039fddcdb8
Operator backend functions overview:
https://www.loom.com/share/074ed237ee4e4789a093ca87e04a1360

## Sprints (tasks)
estimated coding hours required | Sprint # | Sprint short description | front/back | priority | Functions explained | link to screenshot or demo URL | assigned to | completion rate
| 1 | edit splitmenu on Simbalotto | F | 1 | create a splitmenu with 5 dedicated URLs Play/Syndicate/Results/Info/News per every lottery | https://redfoxlotto.com/play/powerball/
| 2 | Wordpress simbalotto.com check play function current status | F | 1 | How was the integration of the ticket grid (numbers picker), lottery info, lottery results solved? How can this be used when more lotteries will be added? | https://simbalotto.com/lotteries/us-powerball/
| 3 | Databases setup | B | 1 | create and set up all databases and data fields. Question: separate databases for players, tickets etc.? | see Excel tab "database!
| 4 | Framework CRM/Backend, Backend Login | B | 1 | Secure login for operator, staff. Captcha, Cloudflare, dedicated IP only | https://www.dropbox.com/s/m4ac768o0o6tu25/operator%20dashboard.jpg?dl=0
| 5 | permission levels | B | 1 | Ability to create usergroups with different permissions for the operator backend. Create a radio button list of important backend functions, combine with permissions to view only /edit/not allowed. We need (at least) one permission level for the operator, one for support staff, one for technical staff (coders). | new function
| 6 | backup routines | B | 1 | permanent backups of the entire project, with the goal of being able to quickly restore | new function
| 7 | Frontend user login | F | 2 | see current frontend | https://www.dropbox.com/s/t88vrt7yngqvtx9/frontend%20customer%20login%20page.jpg?dl=0
| 8 | Frontend user after login | F | 2 | after login displays current balance, nr of tickets not drawn yet | https://www.dropbox.com/s/pecsw2bslch8ou1/User%20area%20overview%20after%20login.jpg?dl=0
| 9 | Frontend user personal data/settings | F | 2 | allow player to complete/edit personal data | https://www.dropbox.com/s/a5ncvrnynjb4jiu/Frontend%20user%20My%20account%20details.jpg?dl=0
| 10 | Frontend user "My tickets" | F | 2 | add Subsections for single tickets, multidraw tickets, syndicate tickets | https://www.dropbox.com/s/vry6pvsfch3hfl0/frontend%20user%20my%20tickets.jpg?dl=0
| 11 | Frontend user "My transactions" | F | 2 | showing player wallet balance, outright ticket purchases, deposits, add: "balance bevor and after transaction" | https://www.dropbox.com/s/wwqx73kako8o6ox/frontend%20user%20my%20transactions.jpg?dl=0
| 12 | User management active/inactive/deleted | B | 2 | List of users, default display: latest signups first. Must be connected to the frontend login/signup functions, see D1. Export to csv. | https://www.dropbox.com/s/17xh81ga1adfavo/operator%20backend%20user%20overview.jpg?dl=0
| 13 | User filters | B | 2 | Filter by language, country, IP, ID, Email, First name, name, signup date range | https://www.dropbox.com/s/17xh81ga1adfavo/operator%20backend%20user%20overview.jpg?dl=0
| 14 | User details display | B | 2 | display ID, name, email, affiliate, agent, balance, country, language, IP address, country of IP, signup date, last active date, nr of purchases, total amount of purchases PLUS export to csv function! | https://www.dropbox.com/s/gal3te73eybk66k/operator%20backend%20display_edit%20user%20details.jpg?dl=0
| 15 | Lottery Play page | F | 2 | display grid of available numbers for picking, quick pick via RNG, multidraw option | https://redfoxlotto.com/play/powerball/
| 16 | Operator backend lottery settings overview | B | 2 | This will show an overview of lotteries, prices etc | https://www.dropbox.com/s/qkr03qa7yi4mle0/operator%20backend%20lottery%20settings%20overview.jpg?dl=0
| 17 | Operator backend edit lottery settings | B | 2 | This will determine which lotteries will be on display for ticket purchase. We will choose from the list of lotteries that Ltech has. Also, here game structure, draw days, hours, pricing, minimum lines, quick pick nr of lines will be set. Some of the lottery-related data will be provided by Ltech (ticket provider). Remark: add to manual setting of price a markup factor solution. See Excel tab "backend for lottery setting" | https://www.dropbox.com/s/8lsjcxujxzerc5y/operator%20backend%20edit%20lottery%20details.jpg?dl=0
| 18 | Operator backend list single tickets | B | 2 | Overview sold tickets, default order showing latest tickets first. Links to user overview, ticket details, transaction details. Export to csv | https://www.dropbox.com/s/pku9imzogf5efiu/operator%20backend%20ticket%20overview.jpg?dl=0
| 19 | Operator backend single ticket details | B | 2 | Ticket details plus uploaded ticket scan | https://www.dropbox.com/s/0trdoxpqvk94k83/operator%20backend%20ticket%20details.jpg?dl=0
| 20 | Operator backend list multidraw tickets | B | 2 | same as above for single tickets, but adapted to multidraw tickets: added display showing data for past draws (win/now win/amounts won), dates of upcoming draws in which the ticket will participate | https://www.dropbox.com/s/uad7pxc0doavhq8/operator%20backend%20multidraw%20ticket%20overview.jpg?dl=0
| 21 | Integration Ltech | B | 2 | This is the integration of the service provider which buys the tickets after customers order them on the website. They also provide the results of the draws via an API, and some basic info about the lotteries. | https://www.dropbox.com/s/aa1c4t67q51sd42/Ltech%20integration%20guide.pdf?dl=0
| 22 | Lotto Results pages, one per each lottery | F | 2 | Showing latest draw results, winnings per tier, draw archive. Integrated with the Wordpress page content! | https://redfoxlotto.com/results/powerball/
| 23 | Lotto Info pages, one per each lottery | F | 2 | Showing draw days/hours, prize tiers, probabilities, guess range, countdown to draw time. Integrated with the Wordpress page content! | https://redfoxlotto.com/lotteries/powerball/
| 24 | Integration Trustpayments | FB | 2 | The most important integration for credit card payments. | Integration guide and API data will be provided later
| 25 | Integration Mpesa | B | 2 | Another integration needed for a payment service provider (PSP) | Integration guide and API data will be provided later
| 26 | Integration Crypto payment | FB | 2 | Another integration needed for a payment service provider (PSP) | Integration guide and API data will be provided later
| 27 | Operator backend Sales reports | B | 2 | Operator can run a full report of sales for a defined time period. Add quick-select dropdown for date ranges like today/yesterday/thismonth etc.Report should show the most important metrics such as sales breakdown by lotteries, breakdown of sales and deposits by payment method used. Link to sales detail page, export to csv | https://www.dropbox.com/s/e3wjfuohz15u8u4/operator%20backend%20full%20sales%20report.jpg?dl=0
| 28 | Operator backend General site settings - frontend display | B | 2 | various settings overview page | https://www.dropbox.com/s/8g3lr5ofjlkh3o0/operator%20backend%20settings%20frontend%20display%20overview.jpg?dl=0
| 29 | Operator backend Mail settings | B | 2 | setup emails which system sends automatically, incl. Translations | https://www.dropbox.com/s/atdjglryju8n7hk/operator%20backend%20settings%20email%20templates%20for%20auto%20emails.jpg?dl=0
| 30 | Operator backend Multidraw settings | B | 2 | set discount percentage when buying multidraw tickets | https://www.dropbox.com/s/8czx6ir4ppm6ns7/operator%20backend%20setting%20for%20discounts%20on%20multidraw%20tickets.jpg?dl=0
| 31 | Operator backend currency settings | B | 2 | set general currency, or currency per country of visitor, suggested amounts for quick deposit | https://www.dropbox.com/s/ywj1x71zqf9qab5/operator%20backend%20setting%20for%20used%20currencies.jpg?dl=0
| 32 | Operator backend Payment methods | B | 2 | show an overview of payment methods, with a link to edit the text that should be shown on the frontend payment page where customers can select the payment method, and the text which should be showing if a payment fails. | https://www.dropbox.com/s/swi5938g7e91qf3/operator%20backend%20lottery%20settings%20payment%20method%20overview.jpg?dl=0
| 33 | Operator backend edit Payment method details | B | 2 | In this area, operator can set and edit the texts about the payment method, as well as all translations for that text | https://www.dropbox.com/s/2mn583fpovx6au7/operator%20backend%20lottery%20settings%20edit%20texts%20for%20payment%20method.jpg?dl=0
| 34 | Operator backend blocked countries | B | 2 | operator can block countries to keep out players from an IP address of that country | https://www.dropbox.com/s/tkak8kno7tm6teb/operator%20backend%20lottery%20settings%20blocked%20countries.jpg?dl=0
| 35 | Operator backend Google Analytics | B | 2 | Operator can enter his GA tracking ID for verification
| 36 | Operator backend Facebook Pixel | B | 2 | Operator can enter a Facebook pixel code for tracking
| 37 | Operator backend Clicky setup | B | 2 | Operator can enter his Clicky ID code for verification
| 38 | Ability to present all frontend functions in xx languages | B | 2 | Wordpress content will be available in multiple languages, but the frontend functions for the sales procedures, player account etc must also be translated. So we need to establish a file holding all those bits of text, so that this file can be exported for translation, and then the translated file can be re-imported to add the new language. This needs to be set up so that, in case of a missing translation, original english would be showing
| 39 | Bonus Management | B | 2 | Define a signup bonus (free ticket after first purchase) and a refer-a-friend bonus, manually add bonus ticket as reward or compensation, or always give bonus ticket to the currently highest jackpot. Also, if player buys a syndicate ticket as first purchase, give him another syndicate ticket as bonus but take a ticket from a block that is approaching draw and does not have all shares sold)
| 40 | User groups | B | 3 | Create groups by setting parameters per month such as sales value , nr of visits, period of inactivity - in short, metrics for targeted customer retention campaigns. Export to csv | new function
| 41 | Aweber integration | B | 3 | add new signups to Aweber subscriber list automatically, as well as auto remove from Aweber players who delete their account | new function
| 42 | Bulk SMS solution | B | 3 | integrate a 3rd party solution for sending out promotional short text messages | new function
| 43 | Lottery Play Syndicate page | F | 3 | must show all options for syndicate play: all available block models with: nr of lines, display all picked numbers, a dropdown where customers can choose how may shares they want to buy, dynamic price info depending on selected options | https://www.dropbox.com/s/gjm02m0ad6xlekg/thelotter_display%20of%20syndicate%20options.jpg?dl=0
| 44 | Backend manage syndicate ticket block purchase | B | 3 | This is where the operator can set up the type of syndicate tickets to be purchased. He must be able to define nr of lines, nr of shares and percentages, sales price per share (via markup factor), cutoff time, should new syndicate blocks be ordered and put omn offer automatically after each draw, option that syndiocate block only be purchased when jackpot is higher than xxx millionauto-repurchase syndicate blocks when sold out (respecting a cutoff time). Also a function to manually purchase a block at any time. See also the tab "Syndicate ticket setup operator" | new function
| 45 | Backend list syndicate tickets | B | 3 | same as above for single tickets, but adapted to syndicate tickets: added display showing nr of lines, how many share bought, total of share in block, percentage of win, (win/no win/amounts won)draws in which the ticket will participate | new function
| 46 | Integration credit card PSP #2 | FB | 3 | Another integration needed for a payment service provider (PSP) | Integration guide and API data will be provided later
| 47 | Integration direct bank transfer | FB | 3 | Another integration needed for a payment service provider (PSP) | Integration guide and API data will be provided later
| 48 | Operator backend overview Transactions | B | 3 | Show all ticket purchases, latest on top by default. Filter by payment method, status (payment successful, payment not completed, payment denied by PSP, reason for denial), filter by ID, User ID, user email, date range. Link to ticket details page, Export to csv | https://www.dropbox.com/s/1xc8356ologzn45/operator%20backend%20transactions%20overview.jpg?dl=0
| 49 | Operator backend transaction details | B | 3 | Transaction details, info about payment method etc. , link to user info, link to ticket details, , add: "balance bevor and after transaction" | https://www.dropbox.com/s/r5ddmbo0lf0dif6/operator%20backend%20transaction%20details.jpg?dl=0
| 50 | Operator backend overview Deposits | B | 3 | Show all money deposits latest on top by default. Filter by payment method, status (payment successful, payment not completed, payment denied by PSP, reason for denial), filter by ID, User ID, user email, date range. Sown link to deposit details page, Export to csv | https://www.dropbox.com/s/u528uwy13hfn3f5/operator%20backend%20deposit%20overview.jpg?dl=0
| 51 | Operator backend overview Withdrawals | B | 3 | Show all requests to withdraw from wallet, latest on top by default. Filter by withdrawal method, status (approved, paid out, payout failed), filter by ID, User ID, user email, date range. Show withdrawal request details page, Export to csv
| 52 | Operator backend Winners Reports | B | 3 | show info about winning tickets by lottery | https://www.dropbox.com/s/qwzv7dmuxaml7ex/operator%20backend%20winners%20report.jpg?dl=0
| 53 | Operators backend for Agent management | B | 3 | Agents will sell lottery tickets from their shops, and those tickets will be printed out on site. All sales via agents must also show in the operator backend, with their statistics, Export to csv | new function
| 54 | Agent sales frontend | F | 3 | A frontend website where an agent can input the customers phone number or email address, select the lottery numbers for him (or use the RNG), define the number of draws in case customer wants a multidraw ticket, then print the ticket and pay via Mpesa. Ticket will be printed on a paper roll printer. There must be a mobile-friendly version of that page for mobile agents with Android phones | new function
| 55 | Agent backend | B | 3 | an area where agents can see their sales stats, add subagents working for them, and see the sug´bagents stats as well | new function
| 56 | Operators Affilate program backend (alternatively, integrate third party software!) | B | 4 | Operator can see his affiliates, activate applications, set affiliate groups, see an overview of commissons generates | make a video!
| 57 | Affiliates backend | B | 4 | Affiliates can see their stats, commissions, generate campaigns, tracked links, download dynamic banners with lotteries and current jackpots
| 58 | Customer support ticket system | B | 4 | Either we create a simple ticket system for customer support, or we intgerate a third-party solution
| 59 | Integration of a chatbot |  | 4 | Integration of a third-party chatbot to assist new customers via AI
| 60 | Operator dashboard | B | 4 | after operator login, show an overview of most important sales stats and metrics, such as registered players, active players this months, sales data etc. , with a date filter function (today/yesterday/this month/ custom period) | https://www.dropbox.com/s/m4ac768o0o6tu25/operator%20dashboard.jpg?dl=0
| 61 | Create a spoofed app-style version of the frontends for customer and agents
0
|  | monthly hours per dev | 160
|  | nr of devs hired | 4
|  | hours per month | 640
|  | months to be needed | 3
suggestion
|  | salary | 80000
|  | bonus after completion | 50000
|  | Total costs bonus | 960000
|  | Total costs salaries | 200000
1160000
9508.1967

## database setup
users | single draw tickets | multidraw tickets | syndicate tickets | purchases | deposits | withdrawals | lotteries
ID nr starting with SLU | ID nr starting with SLT | ID nr starting with SLMT | ID nr starting with SLST | ID nr starting with SLP | ID nr starting with DLD | ID nr starting with SLW | see tab "backend for lottery settings"
Name | User ID nr | User ID nr | User ID nr | User ID nr | User ID nr | User ID nr
Surname | User Name | User Name | User Name | User Name | User Name | User Name
Birthdate | User E-mail | User E-mail | User E-mail | User E-mail | User E-mail | User E-mail
Gender | Payment Method | Payment Method | Payment Method | Payment Method | Payment Method | Withdrawal method
Email | Amount | Amount | Amount | Amount | Amount | User balance
Phone | Date purchase | Date purchase | Date purchase | Date purchase | Date purchase | Amount
Language | Date confirmed | Date confirmed | Date confirmed | Date confirmed | Date confirmed | Date
Timezone | first draw | first draw | first draw | nr of tickets ordered | nr of tickets ordered | Date confirmed
Country |  | last draw | nr of lines on ticket | nr of processed tickets | nr of processed tickets | Status
Region |  | current draw | size of one share | status | status
City | nr of tickets ordered | nr of tickets ordered | cost of ticket block
Address #1 | nr of processed tickets | nr of processed tickets | nr of processed tickets
Address #2 | status | status | status
Postal/ZIP Code
National ID
first registered at which agent
first registered at which affiliate
Currency
Balance
Register date
Register IP
Register country
Last IP
First deposit
Second deposit
Last deposit
Last country
First purchase
Second purchase
Last purchase
First deposit amount
Last deposit amount
Total deposits amount
Total withdrawal
Total purchases amount
Last purchase amount
Total net income
Net winnings
Sale status
System Browser
Last update
Prize payout group
win versus lose quota
Last login to site
Number of purchases
Number of deposits
Time since last purchase or deposit

## syndicate ticket setup operator
Concept for syndicate lottery ticket
Definitions
· A syndicate is a group of lottery players, who purchase a larger number of tickets (lines) and share both the purchase price and the later winnings.
· A line is one combination of numbers
· A package is the totality of the lines for one lottery, created by the operator, which can then be purchased by the players
· A share is a fraction of the package
· Purchase value: sales generated if all shares of a ticket were sold
· Markup means the factor by which the expenses for the lines should be multiplied to set the purchase value of a package.
Example: one line costs €2,00, package contains 30 lines = package cost of €60,00, multiplied by a markup factor of 4,0 = €240,0. If the package were set up to sell as 20 shares, then the purchase price for one share would be €12,00.
Percentage of costs in the above example: €60,00 divided by €240,00 = 25% ticket expenses versus revenue (IF all shares were to be sold!).
Sold vs unsold ratio is another important metric. For the example above, in order to recover the costs of creating a 30 line package, 25% of the shares need to be sold.
If on average 70% of the share of every package could be sold, in the above example, that would mean this:
Cost for one package = €60,00, generated sales = 70% multiplied by €240,00 = €168,00. That means a profit of € 108,00. The costs in this case are € 60,00, sales value € 168,00, which means 35,7% costs on all sales.
This all depends on the markup factor, which should be set high enough, so that the result would be a considerably lower ticket costs on all syndicate sales, more about this later.
I have also set up, and attached to the same email, a basic spreadsheet showing a number of possible packages, and how the number of lines, number of shares and the pricing would influence the profits from syndicates.
Things to consider about the syndicate ticket concept
The main goal of offering syndicates are:
1. To increase ticket sales by offering a product which produces more incidents in which players score a winner. More smaller wins will mean more players will have funds in their player wallets, which will motivate players to come back and play more.
2. To reduce the costs for tickets
The first question is whether it can/should be set up so that packages would be available across multiple whitelabel sites. That would, of course, increase the sold vs unsold shares ratio and result in lower costs. The problem of course is that it is impossible for the individual operator to verify if he has been charged correctly, because he cannot see if and how many shares have been sold via other whitelabels.
Assuming that every whitelabel has their own independent syndicate tickets, the operator has to try and find out how many syndicate shares they can sell, and create their syndicate tickets accordingly. IMO, each operator should take a look at what the average transaction amount is for his clients, and then create attractive packages in that same price range.
Also, it is advisable to start with smaller number of shares, resulting in a better sold vs unsold ratio, and scale the number of shares up after seeing the results.
At which point can an operator add syndicates to his platform?
Let’s assume an operator were to create one 20-line package, sold in 30 shares, for the 5 biggest lotteries only (with, on average, 2 draws per week), at a price of €12,00 and would want to sell at least 50% of the shares in order to make some profit.
That means he has to create 10 packages a week, appr. 40 per month, and sell 15 shares per package. That equals 600 sold shares across all lotteries, at a price of €12 per share. In that case, he would have a revenue of appr. €7200,00 per month from syndicates.
Of course, that means that his current monthly sales (without syndicates) should be considerably higher than €7200,00. Otherwise, he will probably not sell enough shares through his whitelabel, and adding syndicates in a way similar to the example above would not be a profitable move.
But of course, a smaller operator could start out with smaller packages, like offering packages with 10 lines and 15 shares and see how that works. That is why it is of vital importance that each operator is able to set his own parameters in the backend.
If an operator has sufficient traffic and sales, he might even offer multiple package sizes on his site, like 20 lines, 50 lines, 100 lines, and offer “discount” sales prices for the bigger packages.
Pricing
For the setup of each package, operators should be advised that the number of lines should never equal the number of shares. The reason is simple: it would mean that customers can easily compare the price per share with the price for one full ticket ( a 1 out of 20 share for 20 lines offers the same expected value as 1 full ticket) , and thus see that our profit margin is considerably higher for syndicates!
Frontend sales widget
In the frontend, we need a display which shows the details of the packages offered by the operator.
Players can decide which package they want to order (in case there are multiple package sizes), and how many of the shares they want to purchase. Players will very often decide to buy multiple shares, given the relatively low price for one share!
It is also quite important to add the terms for syndicates to the T+C’s, and have the basic information on how syndicates work on the website, and links to that info on the various packages. Maybe even a popup when someone sets out to pay for a syndicate ticket explain that 1 share will only win xx% of the prize. Otherwise, you can expect lots of support requests with questions such as “how does that work” and how much do I win if one of the lines in my 1 share of that package matches 3 numbers” etc.
What is a syndicate ticket?
A syndicate ticket is a share of a ticket which consists of a package of multiple numbers combinations, also called lines. The numbers are predefined by the operator via RNG, so the players cannot choose their own numbers. Players can thus play, for example, 50 number combinations at the same time. Those ticket will then be sold as shares.
I suggest to present the syndicate tickets in the frontend in two ways:
Example: operator orders a ticket with 50 lines, and sets this ticket to be sold in 25 shares. Players can buy shares of 1/25, meaning they will win only 4% of the winningsv on any of the lines.
Advantage: those tickets can be sold at a higher price (or, cost of ticket per share is lower than for a normal ticket. Those tickets arealso very popular with players because they win more often.
Downside: operator must sell at least a certain percentage of the share in order to break even, or make a profit. On the other hand, "leftover" shares could be used for player bonuses
1. A banner across the entire page showcasing the fact that syndicates are available. Banner should contain the most basic info plus a link to a page which explains how syndicate tickets work.
2. An additional tab per each lottery, similar to the tabs “Play -- Results – Information – News”. That tab, similar to the other tabs, should link to a dedicated URL for a page with the sales widget and text. That page can then be SEO’d for keywords such as “Buy syndicate tickets for Euromillions online” (or whatever the operator decides). That opens up a whole range of additional keywords to be targeted, and help drive traffic to the websites.
As long as no packages have been defined for a specific lottery, on that page a message like ”No syndicates available at this time” should be displayed instead of the sales widget.
I suggest to also create three pages to promote special packages consisting of a combination of lines for more than one lottery: 1. Powerball plus Mega Millions (“USA package”), 2. Euromillions plus Eurojackpot (“Europe Package”), 3. “Monster Jackpot Package” (consisting of a combo of the three currently highest jackpots). Those special packages should then also be showcased in the banner mentioned above.
Operator backend for syndicates
Operator must be able to define the details of their own packages (such as xx lines, xx shares, price per share), and decide for which lotteries packages should be offered. It is important that as many steps as possible during the process of generating packages is automatized, so that the operators do not have to manually create those packages 5 times a week!
Also, there must be the option to set a condition for the auto-purchasing of syndicate blocks, namely add a setting that block will only be bought if the jackpot for that lottery is higher than xxx million,
Instead of manually setting the sales price until a desired amount of profit is reached, why not have a box in the column defining the factor (markup) by which the ticket costs are multiplied, which then would set the price accordingly? So if the costs per ticket change for a specific lottery were to change, the sales price would automatically be changed at the same time.
For each lottery, the operator should be able to set, for each lottery, an automatic function which will generate new packages for the next draw, right after the purchase period for the current lottery draw has ended.
At the same time, when all shares for one draw have been sold, the system should automatically generate a new package for the same draw. Operator should be able to set a function defining a time period of xx hours before the draw when no new packages will be auto-created (to avoid having a package created for which not enough shares can be sold to break even!).
Manual creating of packages must be possible. This is important so that when the operator plans to send out an email promoting a specific syndicate package, he can create/define the necessary package(s) to be offered, and if he wants to, he can set a dedicated price.
This could be used to improve conversions: for example, players who signed up but never made a purchase could receive an email with an offer of a special package at a discounted price.
As to the pricing, I suggest that you should consider to have a function to set a modest (automatic) price reduction for unsold shares when the lottery approaches the cut-off time for the draw.
Also, consider a function to auto-generate packages per each lottery ONLY when jackpot is higher than x

## backend for lottery settings
Function (in the backend to add and manage lotteries for which tickets will be sold in the frontend) | type of data | data provided by | comments | where visible in frontend
Lottery ID number | number | manual input during setup
Name of lottery | text | manual input during setup
Currency | dropdown list with currencies | manual input during setup
Country | dropdown list with countries | manual input during setup
Timezone | timezone definition | manual input during setup
weekly draw days | Radio buttons Mo-Sun | manual input during setup
Draw time (local) | hour | manual input during setup
Draw time (CET) | weekday, hour | manual input during setup
Cutoff time | nr of hours | manual input during setup | stops ticket sales at x hours before draw
Next draw date |  | auto-update based on current time
Current jackpot |  | from Ltech API
Range of main numbers | example: from 1 to 49 | manual input during setup or from Ltech API
Range of additional numbers (1) | example: from 1 to 10 | manual input during setup or from Ltech API
Range of additional numbers (2) | example: from 1 to 10 | manual input during setup or from Ltech API
Purchase prize (retail) per ticket | amount in € | from Ltech API
Sales prize per ticket | amount in € | set manually by operator here, or defined by retail prize multiplied by markup factor
Display tiers for winning and (average) prize won |  |  |  | Example:
probability, prize, condition for win tier 1 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 2 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 3 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 4 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 5 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 6 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 7 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 8 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 9 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/
probability, prize, condition for win tier 10 |  | from Ltech API |  | https://redfoxlotto.com/lotteries/mega-millions/

## about sales widgets back+front
The backend contains an area where an unlimited number of lotteries can be added.
The various characteristics of the lotteries can be set and edited here by the operator, unless those metrics are defined and provide by Ltech, the lottery ticket service
In order to display each of the lotteries and their data in the frontend, I need a number of widgets: | example see here:
1 Play widget - showing an area where players can select/edit numbers, run a random numbers generator, set how many draws they want to play | https://redfoxlotto.com/play/mega-millions/
2 Syndicate ticket widget: a syndicate ticket is a predefined number of tickets with pre-chosen numbers, split in xx shares which players can buy | https://www.thelotter.com/lottery-tickets/eurojackpot/?player=0
3 Information widget - showing most important facts of the lottery | https://redfoxlotto.com/lotteries/mega-millions/
4 Results widget - showing the resultsof the last draw, and the past results archive | https://redfoxlotto.com/results/mega-millions/
For any of the lotteries which are added to the system, all four of the above widgets will be needed
Each lottery will have four pages (play/syndicate/info/results) in a Wordpress installation, with dedicated URLs. The pages will then show the corresponding widgets from the above list
This is important because on each page, along with the info defined by the widget, there will be SEO'd text as well, which will drive traffic to the site
That way, I can optimize one page/URL for "play Mega Millions online", one for "Mega Millions syndicate tickets", etc.